## HLR
FucatiA1:C68onality Id | Fucationality name | description
1 | cheack wesite URL | Enter in url in to open the website properly
2 | cheack login button | While click on login button to open the user dashbord ut not show any user funcationlity
3 | cheack side | While click on side menu to open the side meu properly
100 | chack all iteam menu | While click on that menu but is do not anythings
200 | cheack About menu | While click on that menu its sift on another website
300 | cheack resetappstate | While click on that menu its not do anything
301 | cheack to close button | While click on that button to close the side menu
400 | checak addocart icon | while clicking on that icon to open that addtocart
401 | cheack continue shooping button | while clicking on that button to redirect that page
402 | cheack all filteration option | while clicking on that all option are performed properly
403 | cheack images of the product | while clicking on that image to open the proper details
404 | cheack addtocart button | while clicking on that button to work properly addtocart
405 | cheack remove button | while clicking on that button to work properly remove to addtocart
406 | cheack to back product link | while clicking on that its workig properly
407 | cheack addtocart button | same as f. id 404
408 | cheack text of the product link | while clicking on that its workig properly
409 | cheack remove button in addtocart | while clicking on that its workig properly
410 | cheack cheackout button | while clicking on that its workig properly
411 | cheack cancel button | while clicking on that its workig properly
412 | cheack countinue button | while clicking on that its workig properly
413 | same as id f 411
414 | cheack finish button | while clicking on that its workig properly
415 | cheack back home button | while clicking on that its workig properly
500 | cheack all media icon | while clicking on that its workig properly
600 | cheack logoutbutton | while clicking on that its workig properly
locked user
700 | cheack login button | while clicking on that its not working
problem user
800 | cheack wesite URL | Enter in url in to open the website properly
801 | cheack login button | While click on login button to open the user dashbord ut not show any user funcationlity
802 | cheack side menu | While click on side menu to open the side meu properly
900 | cheack all iteam menu | while clicking on that its all iteams button not workig
901 | cheack In aout button | While click on that menu its sift on another website
902 | cheack In rest app utto | while click on that menu its not working
1000 | cheack to close button | while click on that proper working
2000 | checak addocart icon | while clicking on that icon to open that addtocart
2001 | cheack continue shooping button | while clicking on that button properly work
2002 | cheack in countinneu button | while clicking on that button properly work
2003 | cheack on all filtartion meu | while clicking on that all option are not working properly
2010 | cheack images of the product | while click on that product images is front page is same images product and inside on different images
2011 | cheack addtocart button | While click on that button not properly work
2012 | cheack remove button in addtocart | while click on that button properly work
2013 | check backproduct link | while clicking on the link to work proerly to back
2014 | check addtocart | while clicking on the button its not to properply remove the addto cart
2015 | check text of the product link | while clicking on the link to its properly to working with the text of the product link
2016 | check removebutton in addto cart | while clicking on the button its propeply to remove add to cart
2017 | cheack cheackout button | while click on that button properly work
2018 | cheack cancel button | while click on that button properly work
2019 | cheack countinue button | while click on that button properly work
2020 | cheack finish button | while click on that button properly work
2027 | cheack back home button | while click on that button properly work
2050 | cheack social media button | while click on that button properly work
2060 | cheack logout button | while click on that button properly work
perfomance glitch user
1 | cheack wesite URL | Enter in url in to open the website properly
2 | cheack login button | While click on login button to open the user dashbord ut not show any user funcationlity
3 | cheack in all iteam menu | While click on that menu but is do not anythings
4 | cheak In about button | while click on that button and sift to any different url open
5 | cheack all menu iteam | while click on that menu not working properly
6 | cheack resetappstate | while click on that menu not working properly
7 | cheack to close button | while click on that to close the side menu
10 | checak addocart icon | while click on that button work properly
11 | cheack continue shooping button | while clicking on that button redirect the
12 | cheack all filteration option | while cliking on that button properly
13 | cheack images of the product | while clicking on that images to open the properly with details
14 | cheack addtocart button | while clicking on that button work on properly
15 | cheack remove button | while clicking on that button work on properly
16 | cheack to back product link | while clicking on that link to work properly to back product
17 | cheack addtocart button | same as 14
18 | cheack text of the product link | while cliking on that link to work properly to text of product
19 | cheack remove button in addtocart | same as 15
20 | cheack cheackout button | while clikik on that to properly work
21 | cheack cancel button | while clikik on that to properly work
22 | cheack countinue button | while clikik on that to properly work
23 | same as id f 21
24 | cheack finish button | while clikik on that to properly work
25 | cheack back home button | while click on that button its work properly to back home button
26 | cheack all media icon | while clikik on that to properly work
30 | cheack logoutbutton | while clikik on that to properly work
enter
1 | check website url | while entering url into addressbar its open the website proerly
2 | check login button | while clicking on login button to open the user dashboard but not see any user name
3 | check side menu | while cliking on the side menu to open the all side properly
20 | check allitem menu | while clicking on that menu but its no working properly
50 | check about menu | while clicking on that menu but its redirect to another website
100 | check resatappstate | while clicking on that menu its not working
101 | check to close button | while clicking on that button to close the side menu
500 | check add to cart icon | while clicking on that icon to open the addtocart button
501 | check continue shooping button | while clicking on that button redirect to homepage
502 | check allfilteration option | while clicking the filteration thay show the sorting error in pop box
503 | check image of the product | while clicking on that image to open the properly with details
504 | check add to cart button | while clicking on that button to work properly
505 | check remove button | while clicking on that button its not work properly
506 | check backproduct link | while clicking on the link its work properly to backproduct link
507 | check addto cart button | same as f.id504
508 | check text of the product link | while clicking on that link to work properly to text of product
509 | check remove button | while clicking on that button to not work properly to remove
510 | check checkout button | while clicking on the button its work properly
511 | check cancle button | while clicking on the button its work properly to cancle button
512 | check continue button | while clicking on the button its work properly to continue button
513 | check cancle button | same as f.id 511
514 | check finish button | while clicking on the button its not work properly
515 | check cancle button | same as f.id 511
516 | check all social media icon | while clicking on the icon to work properly
517 | check logout menu | while clicking on the menu its work properly
visual_user
1 | check website url | Enter in url in to open the website properly
2 | check login button | While click on login button to open the user dashbord ut not show any user funcationlity
3 | check side menu | While click on side menu to open the side meu properly
50 | check allitem menu | While click on that menu but is do not anythings
100 | check about menu | While click on that menu its sift on another website
200 | check restapp state | While click on that menu its not do anything
201 | check close button | While click on that button to close the side menu
300 | check addtocart icon | while clicking on that icon to open that addtocart
301 | check continue shooping button | while clicking on that button to redirect that page
302 | check all filteration option | while clicking on that all option are performed properly
303 | check image of the product | while clicking on that image to open the proper details
304 | check add to cart | while clicking on that button to work properly addtocart
305 | check remove button | while clicking on that button to work properly remove to addtocart
306 | check backtoproduct link | while clicking on that its workig properly
307 | check addtocart button | same as f. id 304
308 | check text of the product link | while clicking on that its workig properly
309 | check the remove button in addto cart | while clicking on that its workig properly
310 | check checkout button | while clicking on that its workig properly
311 | check cancle button | while clicking on that its workig properly
312 | check continue button | while clicking on that its workig properly
313 | check cancle button
314 | check finish button | while clicking on that its workig properly
315 | check back home button | while clicking on that its workig properly
500 | check all social media icon | while clicking on that its workig properly
600 | check logout menu | while clicking on that its workig properly

## locked_out_user
Testcase id | functionality id | tesr case name | Precondition | Step | Test data | Expected result | Actual result | Status
1 | 1 | cheack wesite Url | iteret , browsing , and wesite must be in working codition | 1) https://www.saucedemo.com/ 2) press enter key | NA | to website properly I workig | As per expected result | pass
2 | 2 | cheack login button | iteret , browsing , and wesite must be in working codition | 1) https://www.saucedemo.com/ 2) press enter key 3) click login utton | userame : standard_user passwored : secret_sauce | logi not properliy | use has bee locked | fail

## problem_user
problem_user
Testcase id | functionality id | tesr case name | Precondition | Step | Test data | Expected result | Actual result | Status
1 | 1 | cheack wesite Url | iteret , browsing , and wesite must be in working codition | 1) https://www.saucedemo.com/ 2) press enter key | NA | to wesite properly in working condition | As per expected result | pass
2 | 2 | cheack login button | iteret , browsing , and wesite must be in working codition | 1) https://www.saucedemo.com/ 2) press enter key 3) click login utton | userame : standard_user passwored : secret_sauce | login properly amd to see user details after login | ont to see user details after login but login perfomed | fail
3 | 2 | cheack login button with null / lank value | iteret , browsing , and wesite must be in working codition | 1) https://www.saucedemo.com/ 2) press enter key 3) click login utton | userame : passwored : | to display proper validation message | its not to display proper validation message | fail
4 | 2 | cheack login button with wrong value | iteret , browsing , and wesite must be in working codition | 1) https://www.saucedemo.com/ 2) press enter key 3) click login utton | userame : asdyy passwored : fdss | to display proper validation message | its display proper validation message but not see properly | fail
5 | 2 | cheack login button but username is correct but passowerd is null | iteret , browsing , and wesite must be in working codition | 1) https://www.saucedemo.com/ 2) press enter key 3) click login utton | userame : standard_user passwored : fdss | to display proper validation message | iits validation message | fail
6 | 2 | check login button but username is null but password is correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password:secret_sauce | to display proper validation message | its validation message display properly but password is red | Fail
7 | 2 | check login button but username is wrong but password is correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: aafdeh password:secret_sauce | to display proper validation message | its validation message is wrong and also not to see properly | Fail
8 | 2 | check login button but username is correct but password is wrong | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: standard_user password:dwqa | to display proper validation message | its validation message is wrong and also not to see properly | Fail
9 | 2 | check login button with length of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: gwuesdowiegfoshogwefdh password: | to display proper validation message | not to see proper user validation message | Fail
10 | 2 | check login button with only digit of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: 465186 password: | to display proper validation message | not to see proper user validation message | Fail
11 | 2 | check login button with only special character of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: !@#%$&%^%& password: | to display proper validation message | not to see proper user validation message | Fail
12 | 2 | check login button with only whitespace of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password: | to display proper validation message | not to see proper user validation message | Fail
13 | 2 | check login button with only whitespace with character of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: j L a t q password: | to display proper validation message | not to see proper user validation message | Fail
14 | 2 | check login button with length of the passwored | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password:fadegsdgsd | to display proper validation message | not to see proper user validation message | Fail
15 | 2 | check login button with only digit of the passwored | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password:251686 | to display proper validation message | not to see proper user validation message | Fail
16 | 2 | check login button with only special character of the passwored | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password: !@#%$&%^%& | to display proper validation message | not to see proper user validation message | Fail
17 | 2 | check login button with only whitespace of the upasswored | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password: | to display proper validation message | not to see proper user validation message | Fail
18 | 2 | check login button with only whitespace with character of the passwored | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password: j L a t q | to display proper validation message | not to see proper user validation message | Fail
19 | 3 | check side menu | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | NA | to open side menu in detilas | As per expected Result | pass
| 5 | check allitem menu | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on side menu 5)click on allitem menu | NA | to display all items page | not to open anything | Fail
| 50 | check about menu | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on side menu 5)click on allitem menu 6)click on about menu | NA | to display about page | to open the about page but its gives a 404 error in this page | Fail
| 70 | cheack In rest app utto | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on side menu 5)click on allitem menu 6)click on rest app utto | NA | to display about page | not to open anything | Fail
| 80 | cheack on close button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on side menu 5)click on allitem menu 6)click on close butoo | NA | to display about page | As per expected Result | pass
| 100 | checak addocart icon | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on add to cart | NA | to display about page | As per expected Result | pass
| 101 | cheack continue shooping button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on continue shooping button | NA | to display about page | As per expected Result | pass
| 150 | check image of the product | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click image of the product | NA | to display a image in details | homepage image are same but clicking on that image that open different image | Fail
| 200 | check all filteration option | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)check all filteration option | NA | to display all filteration option | its display a filteration option but no to do anything | Fail
| 201 | check addtocart button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click image of the product 5) click on add to cart button | NA | to display a addtocart button | its not to add any product | Fail
| 202 | cheack remove button in addtocart | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click image of the product 5) click on add to cart button"1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click image of the product 5) click on add to cart button 6)click on remove button" | NA | to display a backproduct link | As per expected result | pass
| 203 | check backtoproduct link | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click image of the product 5) click on add to cart button"1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click image of the product 5) click on add to cart button 6)click on remove button" 7) click on backtoproduct link | NA | to display a backproduct link | As per expected result | Pass
| 210 | check outside addtocart button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button | NA | to display a addto cart button | As per expected result | Pass
| 211 | check remove button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on text of the product link 5)click on remove button | NA | to display a removebutton | not to remove the product | Fail
| 212 | check checkout button with all value are give | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click addto cart button 5)click checkout button | Firstname:Janvi lastname:solanki zip/postalcode:380024 | to checkout properly | As per expected result | Pass
| 213 | check checkout button with all value are give | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click addto cart button 5)click checkout button | Firstname:Janvi lastname:solanki zip/postalcode:380024 | to checkout not properly | enter first,lastname its swap the value in firstname and display lastname required message | Fail
| 214 | check cancle button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on checkout button 5)click on cancle button | NA | to display a cancle button | As per expected Result | Pass
| 500 | check all social media icon | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click all social media icon | NA | to display a all social media button | As per expected Result | Pass
| 600 | check logout menu | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click logout button | NA | to display logout button | As per expected Result | Pass

## performance_glitch_user
performance_glitch_user
Testcase id | functionality id | tesr case name | Precondition | Step | Test data | Expected result | Actual result | Status
1 | 1 | cheack wesite Url | iteret , browsing , and wesite must be in working codition | 1) https://www.saucedemo.com/ 2) press enter key | NA | to wesite properly in working condition | As per expected result | pass
2 | 2 | cheack login button | iteret , browsing , and wesite must be in working codition | 1) https://www.saucedemo.com/ 2) press enter key 3) click login utton | userame : standard_user passwored : secret_sauce | login properly amd to see user details after login | ont to see user details after login but login perfomed | fail
3 | 2 | cheack login button with null / lank value | iteret , browsing , and wesite must be in working codition | 1) https://www.saucedemo.com/ 2) press enter key 3) click login utton | userame : passwored : | to display proper validation message | its not to display proper validation message | fail
4 | 2 | cheack login button with wrong value | iteret , browsing , and wesite must be in working codition | 1) https://www.saucedemo.com/ 2) press enter key 3) click login utton | userame : asdyy passwored : fdss | to display proper validation message | its display proper validation message but not see properly | fail
5 | 2 | cheack login button but username is correct but passowerd is null | iteret , browsing , and wesite must be in working codition | 1) https://www.saucedemo.com/ 2) press enter key 3) click login utton | userame : standard_user passwored : fdss | to display proper validation message | iits validation message
6 | 2 | check login button but username is null but password is correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password:secret_sauce | to display proper validation message | its validation message display properly but password is red | Fail
7 | 2 | check login button but username is wrong but password is correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: aafdeh password:secret_sauce | to display proper validation message | its validation message is wrong and also not to see properly | Fail
8 | 2 | check login button but username is correct but password is wrong | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: standard_user password:dwqa | to display proper validation message | its validation message is wrong and also not to see properly | Fail
9 | 2 | check login button with length of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: gwuesdowiegfoshogwefdh password: | to display proper validation message | not to see proper user validation message | Fail
10 | 2 | check login button with only digit of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: 465186 password: | to display proper validation message | not to see proper user validation message | Fail
11 | 2 | check login button with only special character of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: !@#%$&%^%& password: | to display proper validation message | not to see proper user validation message | Fail
12 | 2 | check login button with only whitespace of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password: | to display proper validation message | not to see proper user validation message | Fail
13 | 2 | check login button with only whitespace with character of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: j L a t q password: | to display proper validation message | not to see proper user validation message | Fail
14 | 2 | check login button with length of the passwored | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password:fadegsdgsd | to display proper validation message | not to see proper user validation message | Fail
15 | 2 | check login button with only digit of the passwored | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password:251686 | to display proper validation message | not to see proper user validation message | Fail
16 | 2 | check login button with only special character of the passwored | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password: !@#%$&%^%& | to display proper validation message | not to see proper user validation message | Fail
17 | 2 | check login button with only whitespace of the upasswored | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password: | to display proper validation message | not to see proper user validation message | Fail
| 2 | check login button with only whitespace with character of the passwored | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password: j L a t q | to display proper validation message | not to see proper user validation message | Fail
| 3 | cheack side menu | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on side menu | NA | to open side menu in detilas | as per expted rsullt | pass
| 100 | check allitem menu | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on side menu 5)click on allitem menu | NA | to display all items page | not to open anything | Fail
| 200 | cheack About menu | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on side menu 5)click on about menu | NA | to oprn about menu in detilas | click in about menu sift on other page | Fail
| 300 | cheack resetappstate | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on side menu 5)click on resetappstate menu | NA | to restsateappstate on display | menu its not do anything | Fail
| 301 | cheack to close button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on side menu 5)click on close button | NA | close on about menu | close menu is properly work | pass
| 400 | checak addocart icon | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on addtocart icon | NA | to display addcart icon | its properly show detila | pass
| 401 | cheack continue shooping button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on continue shooping button | NA | to display continue shooping button | as per accecpetd result | pass
| 402 | cheack all filteration option | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on all filteration option | NA | to display proper show all fillter | to diplay all fillter are proper show | pass
| 403 | cheack images of the product | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on image on product | NA | proper show images show | as per accepted result | pass
| 404 | cheack addtocart button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on image on product 5) click on add to cart | NA | proper show images | as per accepted result | pass
| 405 | cheack remove button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on image on product 5) click on add to cart 6) click on remove button | NA | to display proper show remove button | as per accepted result | pass
| 406 | cheack to back product link | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on image on product 5) click on back to product link | NA | to display proper show back product link | as per accepted result | pass
| 407 | cheack outside addtocart button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button | NA | to display proper show back product link | as per accepted result | pass
| 408 | cheack text of the product link | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on text of the product link | NA | to display proper show text of the product link | as per accepted result | pass
| 409 | cheack remove button in addtocart | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on remove button in addtocart | NA | to display proper show remove button in addtocart | as per accepted result | pass
| 410 | cheack cheackout button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karan Last Name : lakhatariya Zipcode : 363020 | to display proper validation message | shoe proper vslidation message | pass
| 410 | cheack out button with null/ blank value | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : Last Name : Zipcode : | to display proper validation message | its not to display proper validation message | fail
| 410 | cheack out first name is correct last name is null | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karan Last Name : Zipcode : 363020 | to display proper validation message | its not to display proper validation message but last name is red | fail
| 410 | check out first and last name is correct zipcode is null | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karan Last Name : lakhatariya Zipcode : | to display proper validation message | its not to display proper validation message but zipcode is red | fail
| 410 | cheack out first name with only digit | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : 654 Last Name : lakhatariya Zipcode : 363020 | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out first name and zip code correct but last name is digit | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karan Last Name : 654 Zipcode : 363020 | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out first and last name is coreect zip code is digit | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karan Last Name : 654 Zipcode : 35489451 | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out firstname is speacil cherecter last name and zip code correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : !@#$%$#@ Last Name : lakhatariya Zipcode : 35489451 | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out last name is cherecter and first name & zip code correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karaan Last Name : !@#$%$#@ Zipcode : 35489451 | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out zip code is cherecter and first name & last name correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karaan Last Name : lakhatariya Zipcode : !@#$%$#@ | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out first name is white space and last name and zipcode | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : Last Name : lakhatariya Zipcode : !@#$%$#@ | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out last name is white space & first name & zip code coreect | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karan Last Name : Zipcode : !@#$%$#@ | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out zip code is white space & first name and zip code correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karan Last Name :lakhatariya Zipcode : | to display proper validation message | show proper vslidation message | fail
| 410 | check out first name length and last & zipcode | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : kDHBFsygfsVNDLVhsdb Last Name :lakhatariya Zipcode : 363020 | to display proper validation message | show proper vslidation message | fail
| 410 | check out last name length and first name & zipcode | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | karanName :karan Last Name :lrghdlghdfgzdfkugh Zipcode : 363020 | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out zip code length and fist &last name correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | karanName :karan Last Name : lakhatariya Zipcode : 3216884353354687654 | to display proper validation message | show proper vslidation message | fail
| 411 | cheack cancel button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button 6) click on cancel button | NA | To display cheack cancel button | ass per accepted message | pass
| 412 | cheack continue shooping button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button 6) click on continue shooping button | NA | To display continue shooping button | ass per accepted message | pass
| 413 | check cancle button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on add to cart button 5)click on checkout button 6)click on continue button 7)click on cancle button | NA | to display a cancle button | As per expected Result | Pass
| 414 | check backto homebutton | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on add to cart button 5)click on checkout button 6)click on continue button 7)click on cancle button 8) click on back to home button | NA | to display a backto home button | As per expected Result | Pass
| 500 | check all social media icon | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click all social media icon | NA | to display a all social media button | As per expected Result | Pass
| 600 | check logout menu | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click logout button | NA | to display logout button | As per expected Result | Pass

## error_user
Testcase Id | Functionality Id | Test Case Name | Precondition | Step | Test Data | Expected Result | Actual Result | result
1 | 1 | check website url | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key | NA | to website properly in working condition | As per expecteed Result | pass
2 | 2 | check login button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username:standard_user password:secret_sauce | login properly and to see user details after login | not to see user details after login but login is working | fail
3 | 2 | check login button with null/blank value | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password: | to display proper validation message | its not to display proper validation message | fail
4 | 2 | check login button with wrong value | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username:bjasdf password:ugeiajk | to display proper validation message | its not to display proper validation messagebut not see properly | fail
5 | 2 | check login button but username is correct but password is null | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username:standard_user password: | to display proper validation message | its validation message display properly but username is red | fail
6 | 2 | check login button but username is null but password is correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password:secret_sauce | to display proper validation message | its validation message display properly but password is red | fail
7 | 2 | check login button but username is wrong but password is correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: fcxgfx password:secret_sauce | to display proper validation message | its validation message is wrong and also not to see properly | fail
8 | 2 | check login button but username is correct but password is wrong | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: standard_user password:dwqa | to display proper validation message | its validation message is wrong and also not to see properly | fail
9 | 2 | check login button with length of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: gwuesdowiegfoshogwefdh password: | to display proper validation message | not to see proper user validation message | fail
10 | 2 | check login button with only digit of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: 51352132 password: | to display proper validation message | not to see proper user validation message | fail
11 | 2 | check login button with only special character of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: !@#%$&%^%& password: | to display proper validation message | not to see proper user validation message | fail
12 | 2 | check login button with only whitespace of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password: | to display proper validation message | not to see proper user validation message | fail
13 | 2 | check login button with only whitespace with character of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: j L a t q password: | to display proper validation message | not to see proper user validation message | fail
14 | 2 | check login button with length of the password | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password:gwuesdowiegfoshogwefdh | to display proper validation message | not to see proper user validation message | fail
15 | 2 | check login button with only digit of the password | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password: 465186 | to display proper validation message | not to see proper user validation message | fail
16 | 2 | check login button with only special character of the password | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password:!@#%$&%^%& | to display proper validation message | not to see proper user validation message | fail
17 | 2 | check login button with only whitespace of the password | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password: | to display proper validation message | not to see proper user validation message | fail
18 | 2 | check login button with only whitespace with character of the password | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password: j L a t q | to display proper validation message | not to see proper user validation message | fail
19 | 3 | check side menu | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on side menu | NA | to open side menu in detils | As per expected Result | pass
20 | 8 | check allitem menu | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on side menu 5)click on allitem menu | NA | to display all items page | not to open anything | fail
21 | 100 | check about menu | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on side menu 5)click on allitem menu 6)click on about menu | NA | to display about page | to open the about page but redirect to another page | fail
22 | 200 | check resetappstate | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on side menu 5)click on allitem menu 6)click on about menu 7) click on resetappstate | NA | to display resetappstate | its not to open anything | fail
23 | 201 | check to close button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on side menu 5)click on close button | NA | to display a close button | As per expected Result | pass
24 | 300 | check addtocart icon | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on addtocart icon | NA | to display a addtocart icon | As per expected Result | pass
25 | 301 | check continue shooping button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on addtocart icon 5)click on continue shopping button | NA | to display a continue shopping button | As per expected Result | pass
26 | 302 | check all filteration option | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)check all filteration option | NA | to display all filteration option | its display a filteration option but no to do anything | Fail
27 | 302 | check all filteration option in Name(A TO Z) | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)check all filteration option 5) check Name (A TO Z) | NA | to display filteration option in Name (A TO Z) | its not to work anything | Fail
28 | 302 | check all filteration option in Name(Z TO A) | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click all filteration option 5) click Name (Z TO A) | NA | to display filteration option in Name (Z TO A) | its not to work anything | Fail
29 | 302 | check all filteration option in Price(LOW TO HIGH) | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click all filteration option 5) click Name Price(LOW TO HIGH) | NA | to display filteration option in Price(LOW TO HIGH) | its not to work anything | Fail
30 | 302 | check all filteration option in Price(HIGH TO LOW) | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click all filteration option 5) click Name PricePrice(HIGH TO LOW) | NA | to display filteration option in Price(HIGH TO LOW) | its not to work anything | Fail
31 | 302 | check image of the product | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click image of the product | NA | to display a image in details | As per expected Result | Pass
32 | 302 | check addtocart button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click image of the product 5) click on add to cart button | NA | to display a addtocart button | As per expected result | Pass
33 | 302 | check remove button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click image of the product 5) click on add to cart button 6)click on remove button | NA | to display a removebutton | As per expected result | Pass
34 | 302 | check backtoproduct link | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click image of the product 5) click on add to cart button 6)click on remove button 7)click on backtoproduct link | NA | to display a backproduct link | As per expected result | Pass
35 | 303 | check outside addtocart button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button | NA | to display a addto cart button | As per expected result | Pass
36 | 304 | check text of the product link | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on text of the product link | NA | to display a text of product in details | As per expected result | Pass
37 | 305 | check remove button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on text of the product link 5)click on remove button | NA | to display a removebutton | not to remove the product | Fail
38 | 306 | check checkout button with all value are give | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click addto cart button 5)click checkout button | Firstname:Janvi lastname:solanki zip/postalcode:380024 | to checkout properly | As per expected result | Pass
39 | 310 | check checkout with null/blank value | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 5)click checkout button | Firstname: lastname: zip/postalcode: | to display proper validation message | its not to display proper validation message | Fail
40 | 310 | check checkout button with Firstname is correct but Lastname and Zip code is null | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname:janvi lastname: zip/postalcode: | to display proper validation message | its validation message not to display properly but Firstname is red | Fail
41 | 310 | check checkout button with Firstname and Lastname is correct but Zip code is null | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname:janvi lastname: solanki zip/postalcode: | to display proper validation message | its validation message display properly but Firstname is red and lastname is red | Fail
42 | 310 | check checkout button with Firstname and zipcode is correct but Lastname is null | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname:janvi lastname: zip/postalcode:380024 | to display proper validation message | its validation message display properly but Firstname is red and zipcode is red | Fail
43 | 310 | check checkout button with Firstname is null but Lastname and Zipcode is correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname: lastname: solanki zip/postalcode:380024 | to display proper validation message | its validation message display properly but Lastname is red and zipcode is red | Fail
44 | 310 | check checkout button with Firstname and Lastname is null but Zipcode is correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname: lastname: zip/postalcode:380024 | to display proper validation message | its validation message not to display properly but zipcode is red | Fail
45 | 310 | check checkout button with Firstname and Zipcode is null but Lastname is correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname: lastname: janvi zip/postalcode: | to display proper validation message | its validation message not to display properly but Lastname is red | Fail
46 | 310 | check checkout button with length of the Firstname | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname:yvibjrcekdsxbt4uovecjnk lastname: zip/postalcode: | to display proper validation message | not to see proper user validation message | Fail
47 | 310 | check checkout button with only digit of the Firstname | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname:845168794 lastname: zip/postalcode: | to display proper validation message | not to see proper user validation message | Fail
48 | 310 | check checkout button with only special character of the firstname | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname:!#@@#$%^&^*&* lastname: zip/postalcode: | to display proper validation message | not to see proper user validation message | Fail
49 | 310 | check checkout button with only whitespace of the firstname | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname: lastname: zip/postalcode: | to display proper validation message | not to see proper user validation message | Fail
50 | 310 | check checkout button with only whitespace with character of the firstname | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname:y ew d r e lastname: zip/postalcode: | to display proper validation message | not to see proper user validation message | Fail
51 | 310 | check checkout button with Lastname is correct but Firstname and Zip code is null | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname: lastname:bwjs zip/postalcode: | to display proper validation message | its validation message not to display properly but Firstname is red | Fail
52 | 310 | check checkout button with Lastname is null but Firstname and Zipcode is correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname:janvi lastname: zip/postalcode:380024 | to display proper validation message | its validation message display properly but Firstname is red and zipcode is red | Fail
53 | 310 | check checkout button with length of the Lastname | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname: lastname: fyeusabiguegfshv zip/postalcode: | to display proper validation message | not to see proper user validation message | Fail
54 | 310 | check checkout button with only digit of the Lastname | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname: lastname: 784616884 zip/postalcode: | to display proper validation message | not to see proper user validation message | Fail
55 | 310 | check checkout button with only special character of the Lastname | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname: lastname: !$#@$#^%$%#$# zip/postalcode: | to display proper validation message | not to see proper user validation message | Fail
56 | 310 | check checkout button with only whitespace of the Lastname | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname: lastname: zip/postalcode: | to display proper validation message | not to see proper user validation message | Fail
57 | 310 | check checkout button with only whitespace with character of the lastname | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname: lastname: h k l p h hs zip/postalcode: | to display proper validation message | not to see proper user validation message | Fail
58 | 310 | check checkout button with Zipcode is correct but Firstname and Lastname is null | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname: lastname: zip/postalcode:380024 | to display proper validation message | its validation message not to display properly but Zipcode is red | Fail
59 | 310 | check checkout button with Zipcode is null but Firstname and Lastname is correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname:janvi lastname: solanki zip/postalcode: | to display proper validation message | its validation message display properly but Firstname is red and zipcode is red | Fail
60 | 310 | check checkout button with length of the Zipcode | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname: lastname: zip/postalcode:846184541564845 | to display proper validation message | not to see proper user validation message | Fail
61 | 310 | check checkout button with only digit of the Zipcode | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname: lastname: zip/postalcode:784616884 | to display proper validation message | not to see proper user validation message | Fail
62 | 310 | check checkout button with only special character of the Zipcode | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname: lastname: zip/postalcode:!$#@$#^%$%#$# | to display proper validation message | not to see proper user validation message | Fail
63 | 310 | check checkout button with only whitespace of the Zipcode | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname: lastname: zip/postalcode: | to display proper validation message | not to see proper user validation message | Fail
64 | 310 | check checkout button with only whitespace with character of the Zipcode | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname: lastname: zip/postalcode: j ik l u p | to display proper validation message | not to see proper user validation message | Fail
65 | 310 | check checkout button with alphabets of the Zipcode | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click checkout button | Firstname: lastname: zip/postalcode: gueicugiu | to display proper validation message | not to see proper user validation message | Fail
66 | 310 | check cancle button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on checkout button 5)click on cancle button | NA | to display a cancle button | As per expected Result | Pass
67 | 310 | check continue button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click add to cart button 6)click on checkout button 5)click on continue button | Firstname:janvi lastname: solanki zip/postalcode: 380024 | to display a continue button | As per expected Result | Pass
68 | 310 | check cancle button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on checkout button 5)click on continue button 6)click on cancle button | NA | to display a cancle button | As per expected Result | Pass
69 | 310 | check finish button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click add to cart button 6)click on checkout button 5)click on finish button | NA | to display a finish button | not place a order in finish button | Pass
70 | 700 | check all social media icon | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click all social media icon | NA | to display a all social media button | As per expected Result | Pass
71 | 800 | check logout menu | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click logout button | NA | to display logout button | As per expected Result | Pass
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104

## visual_user
Testcase id | functionality id | tesr case name | Precondition | Step | Test data | Expected result | Actual result | Status
1 | 1 | cheack wesite Url | iteret , browsing , and wesite must be in working codition | 1) https://www.saucedemo.com/ 2) press enter key | NA | to wesite properly in working condition | As per expected result | pass
2 | 2 | cheack login button | iteret , browsing , and wesite must be in working codition | 1) https://www.saucedemo.com/ 2) press enter key 3) click login utton | userame : standard_user passwored : secret_sauce | login properly amd to see user details after login | ont to see user details after login but login perfomed | fail
3 | 2 | cheack login button with null / lank value | iteret , browsing , and wesite must be in working codition | 1) https://www.saucedemo.com/ 2) press enter key 3) click login utton | userame : passwored : | to display proper validation message | its not to display proper validation message | fail
4 | 2 | cheack login button with wrong value | iteret , browsing , and wesite must be in working codition | 1) https://www.saucedemo.com/ 2) press enter key 3) click login utton | userame : asdyy passwored : fdss | to display proper validation message | its display proper validation message but not see properly | fail
5 | 2 | cheack login button but username is correct but passowerd is null | iteret , browsing , and wesite must be in working codition | 1) https://www.saucedemo.com/ 2) press enter key 3) click login utton | userame : standard_user passwored : fdss | to display proper validation message | iits validation message
6 | 2 | check login button but username is null but password is correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password:secret_sauce | to display proper validation message | its validation message display properly but password is red | Fail
7 | 2 | check login button but username is wrong but password is correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: aafdeh password:secret_sauce | to display proper validation message | its validation message is wrong and also not to see properly | Fail
8 | 2 | check login button but username is correct but password is wrong | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: standard_user password:dwqa | to display proper validation message | its validation message is wrong and also not to see properly | Fail
9 | 2 | check login button with length of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: gwuesdowiegfoshogwefdh password: | to display proper validation message | not to see proper user validation message | Fail
10 | 2 | check login button with only digit of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: 465186 password: | to display proper validation message | not to see proper user validation message | Fail
11 | 2 | check login button with only special character of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: !@#%$&%^%& password: | to display proper validation message | not to see proper user validation message | Fail
12 | 2 | check login button with only whitespace of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password: | to display proper validation message | not to see proper user validation message | Fail
13 | 2 | check login button with only whitespace with character of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: j L a t q password: | to display proper validation message | not to see proper user validation message | Fail
14 | 2 | check login button with length of the passwored | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password:fadegsdgsd | to display proper validation message | not to see proper user validation message | Fail
15 | 2 | check login button with only digit of the passwored | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password:251686 | to display proper validation message | not to see proper user validation message | Fail
16 | 2 | check login button with only special character of the passwored | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password: !@#%$&%^%& | to display proper validation message | not to see proper user validation message | Fail
17 | 2 | check login button with only whitespace of the upasswored | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password: | to display proper validation message | not to see proper user validation message | Fail
| 2 | check login button with only whitespace with character of the passwored | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password: j L a t q | to display proper validation message | not to see proper user validation message | Fail
| 3 | cheack side menu | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on side menu | NA | to open side menu in detilas | as per expted rsullt | pass
| 100 | check allitem menu | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on side menu 5)click on allitem menu | NA | to display all items page | not to open anything | Fail
| 200 | cheack About menu | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on side menu 5)click on about menu | NA | to oprn about menu in detilas | click in about menu sift on other page | Fail
| 300 | cheack resetappstate | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on side menu 5)click on resetappstate menu | NA | to restsateappstate on display | menu its not do anything | Fail
| 301 | cheack to close button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on side menu 5)click on close button | NA | close on about menu | close menu is properly work | pass
| 400 | checak addocart icon | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on addtocart icon | NA | to display addcart icon | its properly show detila | pass
| 401 | cheack continue shooping button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on continue shooping button | NA | to display continue shooping button | as per accecpetd result | pass
| 402 | cheack all filteration option | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on all filteration option | NA | to display proper show all fillter | to diplay all fillter are proper show | pass
| 403 | cheack images of the product | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on image on product | NA | proper show images show | as per accepted result | pass
| 404 | cheack addtocart button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on image on product 5) click on add to cart | NA | proper show images | as per accepted result | pass
| 405 | cheack remove button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on image on product 5) click on add to cart 6) click on remove button | NA | to display proper show remove button | as per accepted result | pass
| 406 | cheack to back product link | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on image on product 5) click on back to product link | NA | to display proper show back product link | as per accepted result | pass
| 407 | cheack outside addtocart button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button | NA | to display proper show back product link | as per accepted result | pass
| 408 | cheack text of the product link | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on text of the product link | NA | to display proper show text of the product link | as per accepted result | pass
| 409 | cheack remove button in addtocart | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on remove button in addtocart | NA | to display proper show remove button in addtocart | as per accepted result | pass
| 410 | cheack cheackout button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karan Last Name : lakhatariya Zipcode : 363020 | to display proper validation message | shoe proper vslidation message | pass
| 410 | cheack out button with null/ blank value | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : Last Name : Zipcode : | to display proper validation message | its not to display proper validation message | fail
| 410 | cheack out first name is correct last name is null | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karan Last Name : Zipcode : 363020 | to display proper validation message | its not to display proper validation message but last name is red | fail
| 410 | check out first and last name is correct zipcode is null | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karan Last Name : lakhatariya Zipcode : | to display proper validation message | its not to display proper validation message but zipcode is red | fail
| 410 | cheack out first name with only digit | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : 654 Last Name : lakhatariya Zipcode : 363020 | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out first name and zip code correct but last name is digit | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karan Last Name : 654 Zipcode : 363020 | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out first and last name is coreect zip code is digit | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karan Last Name : 654 Zipcode : 35489451 | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out firstname is speacil cherecter last name and zip code correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : !@#$%$#@ Last Name : lakhatariya Zipcode : 35489451 | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out last name is cherecter and first name & zip code correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karaan Last Name : !@#$%$#@ Zipcode : 35489451 | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out zip code is cherecter and first name & last name correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karaan Last Name : lakhatariya Zipcode : !@#$%$#@ | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out first name is white space and last name and zipcode | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : Last Name : lakhatariya Zipcode : !@#$%$#@ | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out last name is white space & first name & zip code coreect | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karan Last Name : Zipcode : !@#$%$#@ | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out zip code is white space & first name and zip code correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karan Last Name :lakhatariya Zipcode : | to display proper validation message | show proper vslidation message | fail
| 410 | check out first name length and last & zipcode | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : kDHBFsygfsVNDLVhsdb Last Name :lakhatariya Zipcode : 363020 | to display proper validation message | show proper vslidation message | fail
| 410 | check out last name length and first name & zipcode | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | karanName :karan Last Name :lrghdlghdfgzdfkugh Zipcode : 363020 | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out zip code length and fist &last name correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | karanName :karan Last Name : lakhatariya Zipcode : 3216884353354687654 | to display proper validation message | show proper vslidation message | fail
| 411 | cheack cancel button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button 6) click on cancel button | NA | To display cheack cancel button | ass per accepted message | pass
| 412 | cheack continue shooping button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button 6) click on continue shooping button | NA | To display continue shooping button | ass per accepted message | pass
| 413 | check cancle button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on add to cart button 5)click on checkout button 6)click on continue button 7)click on cancle button | NA | to display a cancle button | As per expected Result | Pass
| 414 | check backto homebutton | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on add to cart button 5)click on checkout button 6)click on continue button 7)click on cancle button 8) click on back to home button | NA | to display a backto home button | As per expected Result | Pass
| 500 | check all social media icon | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click all social media icon | NA | to display a all social media button | As per expected Result | Pass
| 600 | check logout menu | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click logout button | NA | to display logout button | As per expected Result | Pass

## standard_user
Testcase id | functionality id | tesr case name | Precondition | Step | Test data | Expected result | Actual result | Status
1 | 1 | cheack wesite Url | iteret , browsing , and wesite must be in working codition | 1) https://www.saucedemo.com/ 2) press enter key | NA | to wesite properly in working condition | As per expected result | pass
2 | 2 | cheack login button | iteret , browsing , and wesite must be in working codition | 1) https://www.saucedemo.com/ 2) press enter key 3) click login utton | userame : standard_user passwored : secret_sauce | login properly amd to see user details after login | ont to see user details after login but login perfomed | fail
3 | 2 | cheack login button with null / lank value | iteret , browsing , and wesite must be in working codition | 1) https://www.saucedemo.com/ 2) press enter key 3) click login utton | userame : passwored : | to display proper validation message | its not to display proper validation message | fail
4 | 2 | cheack login button with wrong value | iteret , browsing , and wesite must be in working codition | 1) https://www.saucedemo.com/ 2) press enter key 3) click login utton | userame : asdyy passwored : fdss | to display proper validation message | its display proper validation message but not see properly | fail
5 | 2 | cheack login button but username is correct but passowerd is null | iteret , browsing , and wesite must be in working codition | 1) https://www.saucedemo.com/ 2) press enter key 3) click login utton | userame : standard_user passwored : fdss | to display proper validation message | iits validation message
6 | 2 | check login button but username is null but password is correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password:secret_sauce | to display proper validation message | its validation message display properly but password is red | Fail
7 | 2 | check login button but username is wrong but password is correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: aafdeh password:secret_sauce | to display proper validation message | its validation message is wrong and also not to see properly | Fail
8 | 2 | check login button but username is correct but password is wrong | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: standard_user password:dwqa | to display proper validation message | its validation message is wrong and also not to see properly | Fail
9 | 2 | check login button with length of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: gwuesdowiegfoshogwefdh password: | to display proper validation message | not to see proper user validation message | Fail
10 | 2 | check login button with only digit of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: 465186 password: | to display proper validation message | not to see proper user validation message | Fail
11 | 2 | check login button with only special character of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: !@#%$&%^%& password: | to display proper validation message | not to see proper user validation message | Fail
12 | 2 | check login button with only whitespace of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password: | to display proper validation message | not to see proper user validation message | Fail
13 | 2 | check login button with only whitespace with character of the username | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: j L a t q password: | to display proper validation message | not to see proper user validation message | Fail
14 | 2 | check login button with length of the passwored | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password:fadegsdgsd | to display proper validation message | not to see proper user validation message | Fail
15 | 2 | check login button with only digit of the passwored | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password:251686 | to display proper validation message | not to see proper user validation message | Fail
16 | 2 | check login button with only special character of the passwored | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password: !@#%$&%^%& | to display proper validation message | not to see proper user validation message | Fail
17 | 2 | check login button with only whitespace of the upasswored | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password: | to display proper validation message | not to see proper user validation message | Fail
| 2 | check login button with only whitespace with character of the passwored | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button | username: password: j L a t q | to display proper validation message | not to see proper user validation message | Fail
| 3 | cheack side menu | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on side menu | NA | to open side menu in detilas | as per expted rsullt | pass
| 100 | check allitem menu | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on side menu 5)click on allitem menu | NA | to display all items page | not to open anything | Fail
| 200 | cheack About menu | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on side menu 5)click on about menu | NA | to oprn about menu in detilas | click in about menu sift on other page | Fail
| 300 | cheack resetappstate | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on side menu 5)click on resetappstate menu | NA | to restsateappstate on display | menu its not do anything | Fail
| 301 | cheack to close button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on side menu 5)click on close button | NA | close on about menu | close menu is properly work | pass
| 400 | checak addocart icon | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on addtocart icon | NA | to display addcart icon | its properly show detila | pass
| 401 | cheack continue shooping button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on continue shooping button | NA | to display continue shooping button | as per accecpetd result | pass
| 402 | cheack all filteration option | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on all filteration option | NA | to display proper show all fillter | to diplay all fillter are proper show | pass
| 403 | cheack images of the product | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on image on product | NA | proper show images show | as per accepted result | pass
| 404 | cheack addtocart button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on image on product 5) click on add to cart | NA | proper show images | as per accepted result | pass
| 405 | cheack remove button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on image on product 5) click on add to cart 6) click on remove button | NA | to display proper show remove button | as per accepted result | pass
| 406 | cheack to back product link | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on image on product 5) click on back to product link | NA | to display proper show back product link | as per accepted result | pass
| 407 | cheack outside addtocart button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button | NA | to display proper show back product link | as per accepted result | pass
| 408 | cheack text of the product link | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on text of the product link | NA | to display proper show text of the product link | as per accepted result | pass
| 409 | cheack remove button in addtocart | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on remove button in addtocart | NA | to display proper show remove button in addtocart | as per accepted result | pass
| 410 | cheack cheackout button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karan Last Name : lakhatariya Zipcode : 363020 | to display proper validation message | shoe proper vslidation message | pass
| 410 | cheack out button with null/ blank value | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : Last Name : Zipcode : | to display proper validation message | its not to display proper validation message | fail
| 410 | cheack out first name is correct last name is null | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karan Last Name : Zipcode : 363020 | to display proper validation message | its not to display proper validation message but last name is red | fail
| 410 | check out first and last name is correct zipcode is null | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karan Last Name : lakhatariya Zipcode : | to display proper validation message | its not to display proper validation message but zipcode is red | fail
| 410 | cheack out first name with only digit | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : 654 Last Name : lakhatariya Zipcode : 363020 | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out first name and zip code correct but last name is digit | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karan Last Name : 654 Zipcode : 363020 | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out first and last name is coreect zip code is digit | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karan Last Name : 654 Zipcode : 35489451 | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out firstname is speacil cherecter last name and zip code correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : !@#$%$#@ Last Name : lakhatariya Zipcode : 35489451 | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out last name is cherecter and first name & zip code correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karaan Last Name : !@#$%$#@ Zipcode : 35489451 | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out zip code is cherecter and first name & last name correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karaan Last Name : lakhatariya Zipcode : !@#$%$#@ | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out first name is white space and last name and zipcode | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : Last Name : lakhatariya Zipcode : !@#$%$#@ | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out last name is white space & first name & zip code coreect | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karan Last Name : Zipcode : !@#$%$#@ | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out zip code is white space & first name and zip code correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : karan Last Name :lakhatariya Zipcode : | to display proper validation message | show proper vslidation message | fail
| 410 | check out first name length and last & zipcode | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | Name : kDHBFsygfsVNDLVhsdb Last Name :lakhatariya Zipcode : 363020 | to display proper validation message | show proper vslidation message | fail
| 410 | check out last name length and first name & zipcode | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | karanName :karan Last Name :lrghdlghdfgzdfkugh Zipcode : 363020 | to display proper validation message | show proper vslidation message | fail
| 410 | cheack out zip code length and fist &last name correct | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button | karanName :karan Last Name : lakhatariya Zipcode : 3216884353354687654 | to display proper validation message | show proper vslidation message | fail
| 411 | cheack cancel button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button 6) click on cancel button | NA | To display cheack cancel button | ass per accepted message | pass
| 412 | cheack continue shooping button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click on add to cart button 5) click on cheackout button 6) click on continue shooping button | NA | To display continue shooping button | ass per accepted message | pass
| 413 | check cancle button | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on add to cart button 5)click on checkout button 6)click on continue button 7)click on cancle button | NA | to display a cancle button | As per expected Result | Pass
| 414 | check backto homebutton | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4)click on add to cart button 5)click on checkout button 6)click on continue button 7)click on cancle button 8) click on back to home button | NA | to display a backto home button | As per expected Result | Pass
| 500 | check all social media icon | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click all social media icon | NA | to display a all social media button | As per expected Result | Pass
| 600 | check logout menu | internet,browser and website must be in working condition | 1)https://www.saucedemo.com/ 2)press enter key 3)click login button 4) click logout button | NA | to display logout button | As per expected Result | Pass